Trans-Asia Engineers — Capability Statement

Submitted to Contoso Mining Services · EPC Tender · Mahakam Coal Handling

Company Snapshot

| Established | 1996 (29 years) |
| --- | --- |
| Headquarters | Jakarta |
| FY25 revenue | USD 410 million |
| FY25 EBITDA margin | 13.8% |
| In-house engineers | 148 engineers |
| Disciplines | Mechanical, Civil/Structural, E&I, Process, Pipeline, Marine, Commissioning |
| HSE — LTI rate (last 3 yrs) | 0.18 per 200,000 hours |
| Certifications | ISO 9001, ISO 14001, ISO 45001, SMK3, API Q1 |

Reference Projects (last 5 years)

Bukit Asam Coal Train Loadout — USD 92m EPC, 22 months, completed 2024 (4 months late, +9% cost)

Pertamina Refinery Utilities — USD 130m EPC, 28 months, completed 2023

Freeport Concentrate Pipeline — USD 88m EPC, 20 months, completed 2022

MIND ID port handling upgrade — USD 65m EPC, 21 months, completed 2024

Timeline Position vs KAK

Tight on 18-month KAK. Internal estimate 20 months — would request 2-month extension at award. Past projects consistently 3-4 months late.

Commercial Position vs KAK Budget

Above KAK budget. Indicative lump-sum USD 84m (8% above cap). Premium reflects engineering depth and risk buffer.

Why Award Us

Deepest engineering bench among the four bidders

Strongest pipeline and marine capability — relevant if scope grows

Highest financial standing — no liquidity risk

Full digital twin handover offered as standard

Known Gaps / Watch-outs (declared)

Track record of schedule slippage on lump-sum work

Commercial position above KAK cap — requires waiver

Heavy Jakarta footprint — slower site response than local bidders